## Sheet1
CSI4142 Physical Design and Data Staging - Project Planning
Deliverable | Team member(s) responsible | Expected completion date | Actual completion date | Estimate time (hours) to complete | Actual time (hours) to complete | Notes (if any)
Create database instance and tables | Yiwen Liu | 2021-03-09 | 2021-03-09 | 2 | 2
Staging of Date dimension | Chuhao Jia | 2021-02-24 | 2021-02-24 | 1 | 1 | Create an individual date dimension and colonel it for others role-playing dates
Staging of Patient dimension | Chuhao Jia | 2021-02-24 | 2021-02-24 | 1 | 0.5 | Not sure how to use Age group in future so I did not know if I should change the age gourp with symbol "<" and "s" in the end.
Staging of PHU dimension | Chuhao Jia | 2021-02-24 | 2021-02-24 | 1 | 0.1
Staging of Mobility dimension | Yiwen Liu/Chuhao Jia | 2021-02-24 | 2021-02-24 | 1 | 0.1
Staging of Weather dimension | Xiaohan Yu | 2021-02-24 | 2021-02-24 | 2 | 1
Map PHU, Mobility and Weather dimensions | Chuhao Jia | 2021-03-03 | 2021-03-08 | 1 | 1
Staging of Special Measures dimension | Xiaohan Yu | 2021-02-24 | 2021-03-03 | 3 | 5.5 | Reseaching takes longer time than planned. I firstly misunderstood how I should structure the measures. After communicating with TA, I redid it. So It took a long time.
Surrogate key pipeline – including role-playing dates | Chuhao Jia | 2021-03-03 | 2021-03-08 | 1 | 0.1
Staging of fact table – including FKs and measures | Chuhao Jia | 2021-03-03 | 2021-03-08 | 1 | 4 | The function of Values[0] occur overflow error but I cannot figure out the reason so I change another way to get values
Data quality handling and reporting | Chuhao Jia | 2021-03-08 | 2021-03-09 | 1 | 1 | Not all the missing value are fixed. Because I did not know what should we do with all of these value in the next stage. So I just fix the value that I think I understand how would we use in the future
Others - if any